## Sheet1
JYOTHY INSTITUTE OF TECHNOLOGY
PROJECT WORK BREAK DOWN STRUTCTURE
PROJECT TITLE : FIREACH FACIAL IMAGE RECONSTRUCTION USING ELLIPTICAL APPROXIMATION AND CONVEX HULL
| DATE : | B R VINAYRAAJ | SANJAY G M | KRISHNA N B
MILESTONE 1 : UNDERSTANDING ALREADY AVAILABLE TECHNOLOGIES
| 21 - 09 - 2016 | UNDERSTANDING ALREADY AVAILABLE TECHNOLOGIES | UNDERSTANDING ALREADY AVAILABLE TECHNOLOGIES | UNDERSTANDING ALREADY AVAILABLE TECHNOLOGIES
| 22 - 09 - 2016 | UNDERSTANDING ALREADY AVAILABLE TECHNOLOGIES | UNDERSTANDING ALREADY AVAILABLE TECHNOLOGIES | UNDERSTANDING ALREADY AVAILABLE TECHNOLOGIES
| 23 - 09 - 2016 | UNDERSTANDING ALREADY AVAILABLE TECHNOLOGIES | UNDERSTANDING ALREADY AVAILABLE TECHNOLOGIES | UNDERSTANDING ALREADY AVAILABLE TECHNOLOGIES
| 24 - 09 - 2016 | STUDY ABOUT GOLDEN RATIO | LEARN ABOUT FACE ROTATION TECHNIQUES | LEARN FACE PROPORTIONS NEEDED FOR RECONSTRUCTION
| 25 - 09 - 2016 | SUNDAY
| 26 - 09 - 2016 | Unavailable | Unavailable | Unavailable
| 27 - 09 - 2016 | Unavailable | Unavailable | Unavailable
| 28 - 09 - 2016 | STUDY ABOUT ELLITICAL APPROXIMATION | STUDY ABOUT EIGEN FACE ALGORITHM | STUDY ABOUT CONVEX HULL
29 - 09 - 2016
| 30 - 09 - 2016 | APPLY ELLITICAL APPROXIMATION ON TEST IMAGES | APPLY EIGEN FACE ALGORITHM ON TEST IMAGES | APPLY CONVEX HULL CONCEPT ON TEST IMAGE
1 - 10 - 2016
| 2 - 10 - 2016 | INTERNALS
3 - 10 - 2016
4 - 10 - 2016
5 - 10 - 2016
6 - 10 - 2016
7 - 10 - 2016
8 - 10 - 2016
| 9 - 10 - 2016 | SUNDAY
| 10 - 10 - 2016 | NAVARATRI(LITRATURE SURVEY ON IEEE PAPERS)
11 - 10 - 2016
12 - 10 - 2016
13 - 10 - 2016
14 - 10 - 2016
15 - 10 - 2016
| 16 - 10 - 2016 | SUNDAY
| 17 - 10 - 2016 | DOCUMENTATION OF THE PROJECT | CREATE GITHUB REPOSITORY FOR PROJECT AND UPLOAD | PREPARE SOFTWARE REQUIREMENT SPECIFICATION
18 - 10 - 2016
| 19 - 10 - 2016 | WORK COLLABRATION ON GITHUB AND LITRATURE SURVEY DISCUSSION
20 - 10 - 2016
| 21 - 10 - 2016 | PREPARATION FOR PROJECT REVIEW PRESENTATION | PREPARE PRESENTATION | CONTENT AND TEST MODEL PREPARATION
22 - 10 - 2016
| 23 - 10 - 2016 | SUNDAY
| 24 - 10 - 2016 | FACE MEASURMENTS USING IMAGES | STUDY ABOUT CANNY EDGE DETECTOR | STUDY SILHOUETTE EXTRACTION OF IMAGE
25 - 10 - 2016
| 26 - 10 - 2016 | 3D MODELLING OF THE FACE | IMPLEMENTATION OF 2D IMAGE ON 3D MODEL | DOCUMENTATION OF TEST CASE
27 - 10 - 2016
| 28 - 10 - 2016 | STUDY ABOUT 3D TO 2D MAPPING | IMPLEMENTATION OF 3D TO 2D MAPPING | GENERATE FULL TEST CASE OUTPUT
29 - 10 - 2016
| 30 - 10 - 2016 | SUNDAY
| 31 - 10 - 2016 | DEEPAVALI[ STUDY ABOUT LANGUAGES THAT CAN BE USED ]
2016-01-11
2016-02-11
| 2016-03-11 | PREPARATION FOR INTERNALS
2016-04-11
2016-05-11
| 2016-06-11 | SUNDAY
| 2016-07-11 | LAB INTERNALS
2016-08-11
2016-09-11
2016-10-11
2016-11-11
2016-12-11
| 13/11/2016 | SUNDAY
| 14/11/2016 | INTERNALS
15/11/2016
16/11/2016
| 17/11/2016 | TEXTURE MAPPING FOR SELECTED AREAS | FINDING 3D FACE MEASURMENTS | STUDY ON FACE MODELLING
18/11/2016
19/11/2016
| 20/11/2016 | SUNDAY
| 21/11/2016 | STUDY IMAGE BASED RENDERING TECHNIQUES | RECOGNISING FACIAL IMAGE | DETECTING PERCENTAGE OF OCCULATION IN THE IMAGE
22/11/2016
23/11/2016
24/11/2016
25/11/2016
26/11/2016
| 27/11/2016 | EXAMS
28/11/2016
29/11/2016
30/11/2016
2016-01-12
2016-02-12
2016-03-12
2016-04-12
2016-05-12
2016-06-12
2016-07-12
2016-08-12
2016-09-12
2016-10-12
2016-11-12
2016-12-12
13/12/2016
14/12/2016
15/12/2016
16/12/2016
17/12/2016
18/12/2016
19/12/2016
20/12/2016
21/12/2016
22/12/2016
23/12/2016
24/12/2016
25/12/2016
26/12/2016
27/12/2016
28/12/2016
29/12/2016
30/12/2016
31/12/2016
2017-01-01
2017-02-01
2017-03-01
2017-04-01
2017-05-01
2017-06-01
2017-07-01
2017-08-01
2017-09-01
2017-10-01
2017-11-01
2017-12-01
13/1/2017
14/1/2017
15/1/2017
| 16/1/2017 | SUNDAY
| 17/1/2017 | APPLY IMAGE BASED RENDERING TECHNIQUES | APPLY CANNY EDGE DETECTOR | STUDY ABOUT EDGE DETECTION
18/1/2017
19/1/2017
| 20/1/2017 | STUDY ON EDGE SRGMENT | STUDY NOVAL BASED TECHNIQUES | SILHOUETTE FORMING USING EDGE DETECTION
21/1/2017
22/1/2017
| 23/1/2017 | SUNDAY
| 24/1/2017 | CONVERTING 2D IMAGE TO 3D IMAGE | CONSTRUCTING 3D HUMAN FACE MODEL | RESULTANT HUMAN FACE BUILT USING PROPOSED SYSTEM
25/1/2017
26/1/2017
27/1/2017
28/1/2017
29/1/2017
| 30/1/2017 | SUNDAY